## Requirement Testing Template1
Requirement ID | Short Description | Requirement Status | Developers Assigned | Developers Who Completed | Standalone/Dependent | Priority | Critical/Not Critical
1.1 | Authentication System: System shall provide a single login interface for students, faculty, and admins | Complete | Moses | Moses | S: Standalone | 10 | C
1.2 | Authentication System: Username shall be exactly 8 lowercase characters (validation enforced) | Complete | Moses | Moses | D: Needs 1.1 | 10 | C
1.3 | Authentication System: Password shall be exactly 12 characters with 1 upper, 1 lower, 1 numeric, 1 symbol | Complete | Moses | Moses | D: Needs 1.1 | 10 | C
1.4 | Authentication System: JWT token generation with 7-day expiration upon successful login | Complete | Moses | Moses | D: Needs 1.1 | 10 | C
1.5 | Authentication System: JWT token verification middleware for protected routes | Complete | Moses | Moses | D: Needs 1.4 | 10 | C
1.6 | Authentication System: Role-based access control (student/faculty/admin) enforcement | Complete | Moses | Moses | D: Needs 1.5 | 10 | C
1.7 | Authentication System: Automatic redirection to role-specific dashboard after login | Complete | Moses | Moses | D: Needs 1.6 | 9 | C
1.8 | Authentication System: Logout functionality clears JWT token from localStorage | Complete | Moses | Moses | D: Needs 1.4 | 9 | C
1.9 | Authentication System: 401 response triggers automatic logout and redirect to login | Complete | Moses | Moses | D: Needs 1.5 | 9 | C
1.10 | User Accounts: System pre-populated with 10 user accounts (5 students, 3 faculty, 2 admins) | Complete | Moses | Moses | D: Needs Database | 10 | C
1.11 | User Accounts: Student accounts configured with program combinations per requirements (1+0, 1+1, 1+2, 2+1, 2+2) | Complete | Moses | Moses | D: Needs 1.10 | 9 | C
1.12 | User Accounts: Faculty accounts assigned advisees (3, 2, 0 distribution) | Complete | Moses | Moses | D: Needs 1.10 | 9 | C
1.13 | User Profile: GET /api/auth/profile returns authenticated user data with relationships | Complete | Michael | Michael | D: Needs 1.5 | 8 | C
1.14 | User Profile: Student profile includes advisor information (self-referencing User relationship) | Complete | Michael | Michael | D: Needs 1.13 | 8 | C
1.15 | User Profile: Faculty profile includes advisee list with program enrollment data | Complete | Moses | Moses | D: Needs 1.13 | 8 | C
2.1 | Database Schema: System shall have 10 core tables (users, programs, courses, program_courses, prerequisites, user_programs, schedules, approvals, approval_history, notifications) | Complete | Moses | Moses | S: Standalone | 10 | C
2.2 | Database Schema: All tables shall use proper foreign key relationships with referential integrity | Complete | Moses | Moses | D: Needs 2.1 | 10 | C
2.3 | Database Schema: System shall enforce 17 ENUM types for data validation (roles, statuses, priorities, categories) | Complete | Moses | Moses | D: Needs 2.1 | 9 | C
2.4 | Database Schema: program_courses junction table enables many-to-many relationship between programs and courses | Complete | Moses | Moses | D: Needs 2.1 | 10 | C
2.5 | Database Schema: prerequisites table supports course self-referencing relationships (courseId → prerequisiteId) | Complete | Moses | Moses | D: Needs 2.1 | 10 | C
2.6 | Database Schema: users table supports self-referencing advisor relationship (advisorId → users.id) | Complete | Moses | Moses | D: Needs 2.1 | 9 | C
2.7 | Course Catalog: System shall load 57 courses from Wright State catalog (BSCS: 14, BSITC: 16, MTH: 8, BA: 18, shared: 1) | Complete | Moses | Moses | D: Needs 2.1 | 10 | C
2.8 | Course Catalog: Each course record includes code, name, credits, description, semesterOffered | Complete | Moses | Moses | D: Needs 2.7 | 10 | C
2.9 | Course Catalog: CO-OP course (ID 57) exists for blocking co-op semesters in schedules | Complete | Moses | Moses | D: Needs 2.7 | 8 | C
2.10 | Academic Programs: System shall define 4 programs (2 majors: BSCS/BSITC, 2 minors: MTH/BA) | Complete | Moses | Moses | D: Needs 2.1 | 10 | C
2.11 | Academic Programs: Each program record includes code, name, type (major/minor), totalCredits, description | Complete | Moses | Moses | D: Needs 2.10 | 9 | C
2.12 | Prerequisite System: System shall enforce 27 prerequisite relationships across course catalog | Complete | Moses | Moses | D: Needs 2.5, 2.7 | 10 | C
2.13 | Prerequisite System: Each prerequisite relationship specifies minimumGrade requirement (C, D, or Pass) | Complete | Moses | Moses | D: Needs 2.12 | 9 | C
2.14 | Prerequisite System: GET /api/courses returns courses with nested prerequisite chains | Complete | Michael | Michael | D: Needs 2.12 | 9 | C
2.15 | Course Search: GET /api/courses/search supports filtering by query, program, credits, semester, hasPrereq | Complete | Michael | Michael | D: Needs 2.7 | 8 | C
2.16 | Course Details: GET /api/courses/:id returns single course with prerequisites and program associations | Complete | Michael | Michael | D: Needs 2.7 | 8 | C
2.17 | Program Courses: GET /api/programs/:id/courses returns all courses for specific program with prerequisite data | Complete | Michael | Michael | D: Needs 2.4, 2.10 | 9 | C
2.18 | Database Migrations: All 13 migration files execute successfully with proper rollback support | Complete | Moses | Moses | D: Needs 2.1 | 9 | C
3.1 | Student Profile API: GET /api/student/profile returns student data with advisor and enrolled programs | Complete | Michael | Michael | D: Needs 1.5, 2.1 | 9 | C
3.2 | Student Programs API: GET /api/student/programs returns active program enrollments with status | Complete | Michael | Michael | D: Needs 3.1 | 9 | C
3.3 | Student Programs API: GET /api/student/available-programs returns catalog of majors and minors | Complete | Michael | Michael | D: Needs 2.10 | 8 | C
3.4 | Program Change Request: POST /api/student/programs/request creates approval request for add/remove | Complete | Michael | Michael | D: Needs 3.2 | 9 | C
3.5 | Program Change Request: System prevents duplicate pending requests for same program | Complete | Moses | Moses | D: Needs 3.4 | 8 | C
3.6 | Program Change Request: System automatically assigns request to student's advisor (facultyId) | Complete | Moses | Moses | D: Needs 3.4, 1.12 | 9 | C
3.7 | Student Schedule API: GET /api/student/schedule returns courses grouped by semester and year | Complete | Michael | Michael | D: Needs 2.1 | 9 | C
3.8 | Student Schedule API: Schedule includes course details, credits, status, and prerequisite data | Complete | Michael | Michael | D: Needs 3.7, 2.12 | 9 | C
3.9 | Add Course to Schedule: POST /api/student/schedule creates schedule entry with validation | Complete | Michael | Michael | D: Needs 3.7 | 9 | C
3.10 | Add Course to Schedule: System validates course not already in same semester/year (duplicate prevention) | Complete | Moses | Moses | D: Needs 3.9 | 9 | C
3.11 | Add Course to Schedule: System blocks adding regular courses to semesters with CO-OP course (ID 57) | Complete | Moses | Moses | D: Needs 3.9, 2.9 | 8 | C
3.12 | Modify Schedule: PUT /api/student/schedule/:id allows changing semester, year, or status | Complete | Michael | Michael | D: Needs 3.7 | 8 | C
3.13 | Remove Course: DELETE /api/student/schedule/:id removes course from schedule | Complete | Michael | Michael | D: Needs 3.7 | 8 | C
3.14 | Course Eligibility: GET /api/student/eligibility/:courseId checks prerequisite completion | Complete | Michael | Michael | D: Needs 2.12 | 9 | C
3.15 | Course Eligibility: System verifies all prerequisites completed with minimum grade requirements | Complete | Moses | Moses | D: Needs 3.14, 2.13 | 9 | C
3.16 | Eligible Courses List: GET /api/student/eligible-courses returns courses student can take based on completion | Complete | Michael | Michael | D: Needs 3.14 | 8 | C
3.17 | Graduation Timeline: GET /api/student/graduation-timeline calculates completion estimate | Complete | Michael | Michael | D: Needs 3.2, 3.7 | 9 | C
3.18 | Graduation Timeline: System calculates total credits required across all enrolled programs | Complete | Moses | Moses | D: Needs 3.17 | 9 | C
3.19 | Graduation Timeline: System calculates completed credits from schedules with status='completed' | Complete | Moses | Moses | D: Needs 3.17 | 9 | C
3.2 | Graduation Timeline: System estimates remaining semesters based on typical 15 credit/semester load | Complete | Moses | Moses | D: Needs 3.17 | 8 | C
3.21 | Co-op Request: POST /api/student/coop/request creates approval with timeline impact analysis | Complete | Michael | Moses | D: Needs 3.17 | 8 | C
3.22 | Co-op Request: GET /api/student/coop/status returns pending and processed co-op requests | Complete | Michael | Moses | D: Needs 3.21 | 7 | C
4.1 | Faculty Advisees API: GET /api/faculty/advisees returns students assigned to logged-in faculty | Complete | Michael | Moses | D: Needs 1.6, 1.12 | 9 | C
4.2 | Faculty Advisees API: Advisee data includes program enrollment, academic progress, and status | Complete | Michael | Moses | D: Needs 4.1 | 9 | C
4.3 | Faculty Approvals API: GET /api/faculty/approvals/pending returns approval requests for faculty's advisees | Complete | Michael | Moses | D: Needs 4.1 | 9 | C
4.4 | Faculty Approvals API: GET /api/faculty/approvals/history returns completed approval decisions | Complete | Michael | Moses | D: Needs 4.3 | 8 | C
4.5 | Approve Request: POST /api/faculty/approvals/:id/approve processes program/schedule/coop approvals | Complete | Michael | Moses | D: Needs 4.3 | 10 | C
4.6 | Approve Request: System automatically updates user_programs table for approved program changes | Complete | Moses | Moses | D: Needs 4.5 | 9 | C
4.7 | Deny Request: POST /api/faculty/approvals/:id/deny rejects request with required reason/comments | Complete | Michael | Moses | D: Needs 4.3 | 9 | C
4.8 | Deny Request: System validates comments field is not empty before allowing denial | Complete | Moses | Moses | D: Needs 4.7 | 8 | C
4.9 | Faculty Schedule Review: GET /api/faculty/schedules/:studentId returns student's complete schedule | Complete | Michael | Moses | D: Needs 4.1, 3.7 | 9 | C
4.10 | Faculty Schedule Amendment: POST /api/faculty/schedules/:studentId/amend allows course modifications | Complete | Moses | Moses | D: Needs 4.9 | 9 | C
4.11 | Schedule Amendment: System supports actions (move_course, add_course, remove_course) | Complete | Moses | Moses | D: Needs 4.10 | 9 | C
4.12 | Schedule Amendment: System verifies student is faculty's advisee before allowing modifications | Complete | Moses | Moses | D: Needs 4.10 | 10 | C
4.13 | Co-op Review: GET /api/faculty/coop/pending returns co-op requests for faculty's advisees | Complete | Michael | Moses | D: Needs 4.1 | 8 | C
4.14 | Co-op Decision: POST /api/faculty/coop/:id/decision processes approve/deny with timeline analysis | Complete | Michael | Moses | D: Needs 4.13 | 9 | C
4.15 | Co-op Approval: System creates CO-OP course (ID 57) schedule entry to block semester on approval | Complete | Moses | Moses | D: Needs 4.14, 2.9 | 9 | C
4.16 | Faculty Program Management: GET /api/faculty/programs returns all programs with course lists | Complete | Michael | Moses | D: Needs 2.10 | 7 | C
4.17 | Faculty Program Management: PUT /api/faculty/programs/:id/courses modifies program requirements | Complete | Michael | Moses | D: Needs 4.16 | 8 | C
4.18 | Program Course Modification: System supports add, remove, update actions for program courses | Complete | Moses | Moses | D: Needs 4.17 | 8 | C
4.19 | Program Course Modification: System allows toggling isRequired flag (required/elective status) | Complete | Moses | Moses | D: Needs 4.17 | 7 | C
4.20 | Admin User Management: GET /api/admin/users returns all users with advisor relationships | Complete | Michael | Moses | D: Needs 1.6 | 9 | C
4.21 | Admin User Creation: POST /api/admin/users creates new accounts with validation | Complete | Moses | Moses | D: Needs 4.20 | 9 | C
4.22 | Admin User Update: PUT /api/admin/users/:id updates user data (password optional in edit mode) | Complete | Michael | Moses | D: Needs 4.20 | 9 | C
4.23 | Admin User Deletion: DELETE /api/admin/users/:id removes user with cascade deletion of relationships | Complete | Michael | Moses | D: Needs 4.20 | 8 | C
4.24 | Admin Advisor Assignment: POST /api/admin/assignments assigns/removes students from faculty advisors | Complete | Michael | Moses | D: Needs 4.20 | 9 | C
4.25 | Admin Advisor Assignment: System enforces 10 advisee maximum per faculty member | Complete | Moses | Moses | D: Needs 4.24 | 9 | C
5.1 | Student Program Management UI: ProgramManagement.tsx displays enrolled programs and catalog | Complete | Moses | Moses | D: Needs 3.2, 3.3 | 9 | C
5.2 | Student Course Catalog UI: CourseCatalog.tsx with search filters (program, credits, semester) | Complete | Moses | Moses | D: Needs 2.15 | 9 | C
5.3 | Student Schedule Planner UI: SchedulePlanner.tsx with multi-semester visualization and CRUD | Complete | Moses | Moses | D: Needs 3.7, 3.9 | 10 | C
5.4 | Student Graduation Timeline UI: GraduationTimeline.tsx with circular progress and timeline display | Complete | Moses | Moses | D: Needs 3.17 | 9 | C
5.5 | Faculty Advisee Profile UI: AdviseeProfile.tsx displays assigned students with progress tracking | Complete | Moses | Moses | D: Needs 4.1, 4.2 | 9 | C
5.6 | Faculty Approval Queue UI: ApprovalQueue.tsx and ApprovalHistory.tsx for request management | Complete | Moses | Moses | D: Needs 4.3, 4.4 | 9 | C
5.7 | Faculty Schedule Review UI: ScheduleReview.tsx with conflict detection and amendment suggestions | Complete | Moses | Moses | D: Needs 4.9, 4.10 | 9 | C
5.8 | Faculty Co-op Management UI: CoopManagement.tsx displays requests with timeline impact analysis | Complete | Moses | Moses | D: Needs 4.13, 4.14 | 8 | C
5.9 | Admin User Management UI: UserManagement.tsx and UserForm.tsx for CRUD operations | Complete | Moses | Moses | D: Needs 4.20, 4.21 | 9 | C
5.10 | Admin Assignment Management UI: AssignmentManagement.tsx with capacity tracking and modals | Complete | Moses | Moses | D: Needs 4.24, 4.25 | 9 | C
5.11 | Admin System Overview UI: SystemOverview.tsx displays system health and metrics dashboard | Complete | Moses | Moses | D: Needs 4.20 | 8 | C
5.12 | Admin Integration Testing UI: IntegrationTesting.tsx with 25 automated tests across 5 suites | Complete | Moses | Moses | D: Needs All APIs | 8 | C
5.13 | Notification Backend: GET /api/notifications retrieves user notifications with unread filtering | Complete | Michael | Moses | D: Needs 1.5 | 7 | NC
5.14 | Notification Backend: PUT /api/notifications/:id/read and /read-all mark notifications as read | Complete | Michael | Moses | D: Needs 5.13 | 7 | NC
5.15 | Notification Frontend: NotificationBadge, NotificationCenter, NotificationItem components with auto-polling | Complete | Moses | Moses | D: Needs 5.13, 5.14 | 7 | NC